## Test Case Planning & Execution
TITLE |  |  |  |  | TEST DATE
LABTRACK |  |  |  |  | 2023-07-03
TEST GROUP BY: |  |  | TEST BY |  | TEST EXECUTED BY
NUTRIWISE |  |  | JEPHTHAT JEHOSAPAT LANDICHO |  | 2023-07-03
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | open the Labtrack (LabManagement) | 2023-07-03 | Admin Login Interface Design will be display |  | Passed
1.1 | After the Admin Login interface appear | 2023-07-03 | Admin will Allowed to Login his/her account |  | Passed
1.2 | click (Go to Member page) | 2023-07-03 | User or Borrower Will login their account |  | Passed
1.3 | Click (who haven’t an account) | 2023-07-03 | Create an Account |  | Passed
1.4 | Faculty and students button | 2023-07-03 | Sign up as (Student or as Faculty) |  | Passed
1.5 | Signup | 2023-07-03 | System will send an message or pop-up an message that you are successfully created an account, then the user have a choice to click that message and will proceed to login or will click the back button |  | Passed
1.6 | Borrower Log-in Interface | 2023-07-03 | Login their ID Number |  | Passed
1.7 | Login Button | 2023-07-03 | If the borrower put an wrong ID the system will sent an Message (ID not Exist) If the Borrower put an correct it will proceed to the Dashboard |  | Passed
1.8 | Dashboard | 2023-07-03 | Requesting Item |  | Passed
1.9 | Requesting Interface | 2023-07-03 | Borrower will able to Fill up Requesting Form |  | Passed
2 | Items (maximum of 5 Items) field | 2023-07-03 | Items from inventory will be appear |  | Passed
2.1 | Date and time field | 2023-07-03 | Date and time is automatically set in current date and time |  | Passed
2.2 | Click Selecting Room | 2023-07-03 | Borrower will choose his/her room or section |  | Passed
2.3 | Set Time Limit | 2023-07-03 | Borrower will set the date and time, where will it be returned the item. |  | Passed
2.4 | requesting status | 2023-07-03 | Inside the sidebar, Borrower can see all the requesting item that she do such as pending request, accepted request and Cancel Request. |  | Passed
2.5 | Next and Previous button | 2023-07-03 | Borrower can click the next button if the table is overloaded and previous button if the borrower wants to go back to the previous page |  | Passed
2.6 | Header | 2023-07-03 | Profile and Logout |  | Passed
2.7 | Click Logout | 2023-07-03 | Borrower will exit |  | Passed
2.8 | Open the labtrack system | 2023-07-03 | The system should open as expected |  | Passed
2.9 | After opening the system, it should display the UI for logging in | 2023-07-03 | The login form will be displayed and there are choices if you are a student or faculty or you don’t have an account |  | Passed
3.0 | If you don’t have an account, click the sign up | 2023-07-03 | You will be directed to a sign-up page in which the user will choose if he/she is student/faculty |  | Passed
3.1 | If the user chooses the student there’s a form that needs to be fill up in order to create an account | 2023-07-03 | The user will click submit if all the information is filled up |  | Passed
3.2 | If the user chooses chooses the faculty, he also needs to fill up the form | 2023-07-03 | The user will click submit if all the information is filled up |  | Passed
3.3 | if the user already has an account click the login | 2023-07-03 | Insert users’ credential |  | Passed
3.4 | If the user enters a wrong username or password | 2023-07-03 | A pop up will be displayed saying “username and password are incorrect” |  | Passed
3.5 | If the user enters the right credentials | 2023-07-03 | An alert will be displayed saying “Redirecting, successfully login” |  | Passed
3.6 | After the user clicked the login button | 2023-07-03 | The user will be directed to the admin dashboard and displays the notifications for new borrow request etc |  | Passed
3.7 | at the admin the dashboard click the transaction button | 2023-07-03 | Dropdown list will be displayed such as request, new, borrowed items and returned items |  | Passed
3.8 | Click the request button | 2023-07-03 | A table will be displayed for pending and accepted request. The table contains name, items, the date of request rooms and the action |  | Passed
3.9 | Click the new button | 2023-07-03 | A form will be displayed and must be filled up to borrow equipment, walk in users only |  | Passed
4 | Click the borrowed items | 2023-07-03 | A table will be displayed for borrowed items and the admin can return items if the items borrowed is already returned |  | Passed
4.1 | Click the returned items | 2023-07-03 | A table will be displayed for returned items the table contains borrower name, the returned items, the date and the date returned |  | Passed
4.2 | Click the item button | 2023-07-03 | The user will be directed to the items contained in the inventory |  | Passed
4.3 | Click the add item button | 2023-07-03 | The form to add item will be displayed, the user needed to fill the form in order to add items |  | Passed
4.4 | Click the add button | 2023-07-03 | After clicking the add button an alert will be displayed “Item added” |  | Passed
4.5 | After the click the add button | 2023-07-03 | The item will be displayed on the table |  | Passed
4.6 | Request | 2023-07-03 | Pop up message |  | Failed